## Summary DCS Ingestion Adjustmen
No | Order | Entity | Market Code | Table Name | Status Development DEV | Status Development QAS | Comment (QA) | Comment (PRD)
1 | 1 | DEVICES | DK | DK_DEVICES | Done | Done
2 | 2 | DEVICES | GR | GR_DEVICES | Done | Done
3 | 3 | DEVICES | RO | RO_DEVICES | Done | Done
4 | 4 | DEVICES | PT | PT_DEVICES | Done | Done
5 | 5 | DEVICES | CA | CA_DEVICES | Done | Done
6 | 6 | DEVICES | IT | IT_DEVICES | Done | Done
7 | 7 | DEVICES | AU | AU_DEVICES | Done | Done |  | 0 rows from DISP
8 | 8 | DEVICES | KZ | KZ_DEVICES | Done | Done | 0 rows from DISP
9 | 9 | DEVICES | LT | LT_DEVICES | Done | Done
10 | 10 | DEVICES | NZ | NZ_DEVICES | Done | Done
11 | 11 | DEVICES | SE | SE_DEVICES | Done | Done
12 | 12 | DEVICES | IL | IL_DEVICES | Done | Done
13 | 13 | DEVICES | NL | NL_DEVICES | Done | Done
14 | 14 | DEVICES | UA | UA_DEVICES | Done | Done
15 | 1 | GIFTCERTIFICATES | SE | SE_GIFTCERTIFICATES | Done | Done | 0 rows from DISP | 0 rows from DISP
16 | 2 | GIFTCERTIFICATES | PT | PT_GIFTCERTIFICATES | Done | Done | 0 rows from DISP | 0 rows from DISP
17 | 3 | GIFTCERTIFICATES | IT | IT_GIFTCERTIFICATES | Done | Done |  | 0 rows from DISP
18 | 4 | GIFTCERTIFICATES | NL | NL_GIFTCERTIFICATES | Done | Done |  | 0 rows from DISP
19 | 5 | GIFTCERTIFICATES | RO | RO_GIFTCERTIFICATES | Done | Done
20 | 6 | GIFTCERTIFICATES | AU | AU_GIFTCERTIFICATES | Done | Done | 0 rows from DISP | 0 rows from DISP
21 | 7 | GIFTCERTIFICATES | DK | DK_GIFTCERTIFICATES | Done | Done | 0 rows from DISP | 0 rows from DISP
22 | 8 | GIFTCERTIFICATES | IL | IL_GIFTCERTIFICATES | Done | Done |  | 0 rows from DISP
23 | 9 | GIFTCERTIFICATES | GR | GR_GIFTCERTIFICATES | Done | Done |  | 0 rows from DISP
24 | 10 | GIFTCERTIFICATES | CA | CA_GIFTCERTIFICATES | Done | Done
25 | 11 | GIFTCERTIFICATES | NZ | NZ_GIFTCERTIFICATES | Done | Done | 0 rows from DISP | 0 rows from DISP
26 | 12 | GIFTCERTIFICATES | LT | LT_GIFTCERTIFICATES | Done | Done | 0 rows from DISP | 0 rows from DISP
27 | 13 | GIFTCERTIFICATES | UA | UA_GIFTCERTIFICATES | Done | Done
28 | 14 | GIFTCERTIFICATES | KZ | KZ_GIFTCERTIFICATES | Done | Done | 0 rows from DISP | 0 rows from DISP
29 | 1 | ORDERHISTORY | UA | UA_ORDERHISTORY | Done | Done
30 | 2 | ORDERHISTORY | RO | RO_ORDERHISTORY | Done | Done
31 | 3 | ORDERHISTORY | LT | LT_ORDERHISTORY | Done | Done
32 | 4 | ORDERHISTORY | NL | NL_ORDERHISTORY | Done | Done
33 | 5 | ORDERHISTORY | NZ | NZ_ORDERHISTORY | Done | Done
34 | 6 | ORDERHISTORY | IT | IT_ORDERHISTORY | Done | Done
35 | 7 | ORDERHISTORY | PT | PT_ORDERHISTORY | Done | Done
36 | 8 | ORDERHISTORY | GR | GR_ORDERHISTORY | Done | Done
37 | 9 | ORDERHISTORY | SE | SE_ORDERHISTORY | Done | Done
38 | 10 | ORDERHISTORY | AU | AU_ORDERHISTORY | Done | Done |  | 0 rows from DISP
39 | 11 | ORDERHISTORY | DK | DK_ORDERHISTORY | Done | Done
40 | 12 | ORDERHISTORY | IL | IL_ORDERHISTORY | Done | Done
41 | 13 | ORDERHISTORY | KZ | KZ_ORDERHISTORY | Done | Done | 0 rows from DISP
42 | 14 | ORDERHISTORY | CA | CA_ORDERHISTORY | Done | Done
43 | 1 | ORDERITEMS | AU | AU_ORDERITEMS | Done | Done |  | 0 rows from DISP
44 | 2 | ORDERITEMS | UA | UA_ORDERITEMS | Done | Done
45 | 3 | ORDERITEMS | LT | LT_ORDERITEMS | Done | Done
46 | 4 | ORDERITEMS | NL | NL_ORDERITEMS | Done | Done
47 | 5 | ORDERITEMS | GR | GR_ORDERITEMS | Done | Done
48 | 6 | ORDERITEMS | DK | DK_ORDERITEMS | Done | Done
49 | 7 | ORDERITEMS | CA | CA_ORDERITEMS | Done | Done
50 | 8 | ORDERITEMS | PT | PT_ORDERITEMS | Done | Done
51 | 9 | ORDERITEMS | IL | IL_ORDERITEMS | Done | Done
52 | 10 | ORDERITEMS | KZ | KZ_ORDERITEMS | Done | Done | 0 rows from DISP
53 | 11 | ORDERITEMS | SE | SE_ORDERITEMS | Done | Done
54 | 12 | ORDERITEMS | IT | IT_ORDERITEMS | Done | Done
55 | 13 | ORDERITEMS | NZ | NZ_ORDERITEMS | Done | Done
56 | 14 | ORDERITEMS | RO | RO_ORDERITEMS | Done | Done
57 | 1 | ORDERS | AU | AU_ORDERS | Done | Done |  | 0 rows from DISP
58 | 2 | ORDERS | UA | UA_ORDERS | Done | Done
59 | 3 | ORDERS | LT | LT_ORDERS | Done | Done
60 | 4 | ORDERS | NL | NL_ORDERS | Done | Done
61 | 5 | ORDERS | GR | GR_ORDERS | Done | Done
62 | 6 | ORDERS | DK | DK_ORDERS | Done | Done
63 | 7 | ORDERS | CA | CA_ORDERS | Done | Done
64 | 8 | ORDERS | PT | PT_ORDERS | Done | Done
65 | 9 | ORDERS | IL | IL_ORDERS | Done | Done
66 | 10 | ORDERS | KZ | KZ_ORDERS | Done | Done | 0 rows from DISP
67 | 11 | ORDERS | SE | SE_ORDERS | Done | Done
68 | 12 | ORDERS | IT | IT_ORDERS | Done | Done
69 | 13 | ORDERS | NZ | NZ_ORDERS | Done | Done
70 | 14 | ORDERS | RO | RO_ORDERS | Done | Done
71 | 1 | PROFILEFIELDS | AU | AU_PROFILEFIELDS | Done | Done
72 | 2 | PROFILEFIELDS | UA | UA_PROFILEFIELDS | Done | Done
73 | 3 | PROFILEFIELDS | LT | LT_PROFILEFIELDS | Done | Done
74 | 4 | PROFILEFIELDS | NL | NL_PROFILEFIELDS | Done | Done
75 | 5 | PROFILEFIELDS | GR | GR_PROFILEFIELDS | Done | Done
76 | 6 | PROFILEFIELDS | DK | DK_PROFILEFIELDS | Done | Done
77 | 7 | PROFILEFIELDS | CA | CA_PROFILEFIELDS | Done | Done
78 | 8 | PROFILEFIELDS | PT | PT_PROFILEFIELDS | Done | Done
79 | 9 | PROFILEFIELDS | IL | IL_PROFILEFIELDS | Done | Done
80 | 10 | PROFILEFIELDS | KZ | KZ_PROFILEFIELDS | Done | Done | 0 rows from DISP
81 | 11 | PROFILEFIELDS | SE | SE_PROFILEFIELDS | Done | Done | 0 rows from DISP
82 | 12 | PROFILEFIELDS | IT | IT_PROFILEFIELDS | Done | Done
83 | 13 | PROFILEFIELDS | NZ | NZ_PROFILEFIELDS | Done | Done
84 | 14 | PROFILEFIELDS | RO | RO_PROFILEFIELDS | Done | Done | 0 rows from DISP | 0 rows from DISP
85 | 1 | PROMOTIONS | AU | AU_PROMOTIONS | Done | Done | 0 rows from DISP | 0 rows from DISP
86 | 2 | PROMOTIONS | UA | UA_PROMOTIONS | Done | Done
87 | 3 | PROMOTIONS | LT | LT_PROMOTIONS | Done | Done
88 | 4 | PROMOTIONS | NL | NL_PROMOTIONS | Done | Done
89 | 5 | PROMOTIONS | GR | GR_PROMOTIONS | Done | Done
90 | 6 | PROMOTIONS | DK | DK_PROMOTIONS | Done | Done
91 | 7 | PROMOTIONS | CA | CA_PROMOTIONS | Done | Done
92 | 8 | PROMOTIONS | PT | PT_PROMOTIONS | Done | Done
93 | 9 | PROMOTIONS | IL | IL_PROMOTIONS | Done | Done
94 | 10 | PROMOTIONS | KZ | KZ_PROMOTIONS | Done | Done | 0 rows from DISP
95 | 11 | PROMOTIONS | SE | SE_PROMOTIONS | Done | Done
96 | 12 | PROMOTIONS | IT | IT_PROMOTIONS | Done | Done
97 | 13 | PROMOTIONS | NZ | NZ_PROMOTIONS | Done | Done
98 | 14 | PROMOTIONS | RO | RO_PROMOTIONS | Done | Done
99 | 1 | SEASURVEYS | AU | AU_SEASURVEYS | Done | Done
100 | 2 | SEASURVEYS | UA | UA_SEASURVEYS | Done | Done | 0 rows from DISP
101 | 3 | SEASURVEYS | LT | LT_SEASURVEYS | Done | Done
102 | 4 | SEASURVEYS | NL | NL_SEASURVEYS | Done | Done
103 | 5 | SEASURVEYS | GR | GR_SEASURVEYS | Done | Done
104 | 6 | SEASURVEYS | DK | DK_SEASURVEYS | Done | Done | 0 rows from DISP
105 | 7 | SEASURVEYS | CA | CA_SEASURVEYS | Done | Done
106 | 8 | SEASURVEYS | PT | PT_SEASURVEYS | Done | Done | 0 rows from DISP
107 | 9 | SEASURVEYS | IL | IL_SEASURVEYS | Done | Done
108 | 10 | SEASURVEYS | KZ | KZ_SEASURVEYS | Done | Done | 0 rows from DISP
109 | 11 | SEASURVEYS | SE | SE_SEASURVEYS | Done | Done | 0 rows from DISP
110 | 12 | SEASURVEYS | IT | IT_SEASURVEYS | Done | Done
111 | 13 | SEASURVEYS | NZ | NZ_SEASURVEYS | Done | Done
112 | 14 | SEASURVEYS | RO | RO_SEASURVEYS | Done | Done | 0 rows from DISP | 0 rows from DISP
113 | 1 | SHIPMENTS | AU | AU_SHIPMENTS | Done | Done
114 | 2 | SHIPMENTS | UA | UA_SHIPMENTS | Done | Done | 0 rows from DISP | 0 rows from DISP
115 | 3 | SHIPMENTS | LT | LT_SHIPMENTS | Done | Done
116 | 4 | SHIPMENTS | NL | NL_SHIPMENTS | Done | Done |  | 0 rows from DISP
117 | 5 | SHIPMENTS | GR | GR_SHIPMENTS | Done | Done
118 | 6 | SHIPMENTS | DK | DK_SHIPMENTS | Done | Done
119 | 7 | SHIPMENTS | CA | CA_SHIPMENTS | Done | Done
120 | 8 | SHIPMENTS | PT | PT_SHIPMENTS | Done | Done
121 | 9 | SHIPMENTS | IL | IL_SHIPMENTS | Done | Done
122 | 10 | SHIPMENTS | KZ | KZ_SHIPMENTS | Done | Done | 0 rows from DISP | 0 rows from DISP
123 | 11 | SHIPMENTS | SE | SE_SHIPMENTS | Done | Done
124 | 12 | SHIPMENTS | IT | IT_SHIPMENTS | Done | Done
125 | 13 | SHIPMENTS | NZ | NZ_SHIPMENTS | Done | Done
126 | 14 | SHIPMENTS | RO | RO_SHIPMENTS | Done | Done
127 | 1 | TOUCHPOINTS | AU | AU_TOUCHPOINTS | Done | Done
128 | 2 | TOUCHPOINTS | UA | UA_TOUCHPOINTS | Done | Done
129 | 3 | TOUCHPOINTS | LT | LT_TOUCHPOINTS | Done | Done
130 | 4 | TOUCHPOINTS | NL | NL_TOUCHPOINTS | Done | Done
131 | 5 | TOUCHPOINTS | GR | GR_TOUCHPOINTS | Done | Done
132 | 6 | TOUCHPOINTS | DK | DK_TOUCHPOINTS | Done | Done
133 | 7 | TOUCHPOINTS | CA | CA_TOUCHPOINTS | Done | Done
134 | 8 | TOUCHPOINTS | PT | PT_TOUCHPOINTS | Done | Done
135 | 9 | TOUCHPOINTS | IL | IL_TOUCHPOINTS | Done | Done
136 | 10 | TOUCHPOINTS | KZ | KZ_TOUCHPOINTS | Done | Done | 0 rows from DISP
137 | 11 | TOUCHPOINTS | SE | SE_TOUCHPOINTS | Done | Done
138 | 12 | TOUCHPOINTS | IT | IT_TOUCHPOINTS | Done | Done |  | 0 rows from DISP
139 | 13 | TOUCHPOINTS | NZ | NZ_TOUCHPOINTS | Done | Done
140 | 14 | TOUCHPOINTS | RO | RO_TOUCHPOINTS | Done | Done
141 | 1 | SPENDINGS | AU | AU_SPENDINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
142 | 2 | SPENDINGS | UA | UA_SPENDINGS | Done | Done
143 | 3 | SPENDINGS | LT | LT_SPENDINGS | Done | Done
144 | 4 | SPENDINGS | NL | NL_SPENDINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
145 | 5 | SPENDINGS | GR | GR_SPENDINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
146 | 6 | SPENDINGS | DK | DK_SPENDINGS | Done | Done |  | 0 rows from DISP
147 | 7 | SPENDINGS | CA | CA_SPENDINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
148 | 8 | SPENDINGS | PT | PT_SPENDINGS | Done | Done
149 | 9 | SPENDINGS | IL | IL_SPENDINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
150 | 10 | SPENDINGS | KZ | KZ_SPENDINGS | Done | Done | 0 rows from DISP
151 | 11 | SPENDINGS | SE | SE_SPENDINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
152 | 12 | SPENDINGS | IT | IT_SPENDINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
153 | 13 | SPENDINGS | NZ | NZ_SPENDINGS | Done | Done
154 | 14 | SPENDINGS | RO | RO_SPENDINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
155 | 1 | REFERRALCODEPERGODFATHER | AU | AU_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP | 0 rows from DISP
156 | 2 | REFERRALCODEPERGODFATHER | UA | UA_REFERRALCODEPERGODFATHER | Done | Done
157 | 3 | REFERRALCODEPERGODFATHER | LT | LT_REFERRALCODEPERGODFATHER | Done | Done
158 | 4 | REFERRALCODEPERGODFATHER | NL | NL_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP | 0 rows from DISP
159 | 5 | REFERRALCODEPERGODFATHER | GR | GR_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP | 0 rows from DISP
160 | 6 | REFERRALCODEPERGODFATHER | DK | DK_REFERRALCODEPERGODFATHER | Done | Done
161 | 7 | REFERRALCODEPERGODFATHER | CA | CA_REFERRALCODEPERGODFATHER | Done | Done |  | 0 rows from DISP
162 | 8 | REFERRALCODEPERGODFATHER | PT | PT_REFERRALCODEPERGODFATHER | Done | Done
163 | 9 | REFERRALCODEPERGODFATHER | IL | IL_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP | 0 rows from DISP
164 | 10 | REFERRALCODEPERGODFATHER | KZ | KZ_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP
165 | 11 | REFERRALCODEPERGODFATHER | SE | SE_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP | 0 rows from DISP
166 | 12 | REFERRALCODEPERGODFATHER | IT | IT_REFERRALCODEPERGODFATHER | Done | Done |  | 0 rows from DISP
167 | 13 | REFERRALCODEPERGODFATHER | NZ | NZ_REFERRALCODEPERGODFATHER | Done | Done
168 | 14 | REFERRALCODEPERGODFATHER | RO | RO_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP | 0 rows from DISP
169 | 1 | PRODUCTS | AU | AU_PRODUCTS | Done | Done
170 | 2 | PRODUCTS | UA | UA_PRODUCTS | Done | Done
171 | 3 | PRODUCTS | LT | LT_PRODUCTS | Done | Done
172 | 4 | PRODUCTS | NL | NL_PRODUCTS | Done | Done
173 | 5 | PRODUCTS | GR | GR_PRODUCTS | Done | Done
174 | 6 | PRODUCTS | DK | DK_PRODUCTS | Done | Done
175 | 7 | PRODUCTS | CA | CA_PRODUCTS | Done | Done
176 | 8 | PRODUCTS | PT | PT_PRODUCTS | Done | Done
177 | 9 | PRODUCTS | IL | IL_PRODUCTS | Done | Done
178 | 10 | PRODUCTS | KZ | KZ_PRODUCTS | Done | Done | 0 rows from DISP
179 | 11 | PRODUCTS | SE | SE_PRODUCTS | Done | Done
180 | 12 | PRODUCTS | IT | IT_PRODUCTS | Done | Done
181 | 13 | PRODUCTS | NZ | NZ_PRODUCTS | Done | Done
182 | 14 | PRODUCTS | RO | RO_PRODUCTS | Done | Done | 0 rows from DISP
183 | 1 | EARNINGS | AU | AU_EARNINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
184 | 2 | EARNINGS | UA | UA_EARNINGS | Done | Done
185 | 3 | EARNINGS | LT | LT_EARNINGS | Done | Done
186 | 4 | EARNINGS | NL | NL_EARNINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
187 | 5 | EARNINGS | GR | GR_EARNINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
188 | 6 | EARNINGS | DK | DK_EARNINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
189 | 7 | EARNINGS | CA | CA_EARNINGS | Done | Done
190 | 8 | EARNINGS | PT | PT_EARNINGS | Done | Done
191 | 9 | EARNINGS | IL | IL_EARNINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
192 | 10 | EARNINGS | KZ | KZ_EARNINGS | Done | Done | 0 rows from DISP
193 | 11 | EARNINGS | SE | SE_EARNINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
194 | 12 | EARNINGS | IT | IT_EARNINGS | Done | Done
195 | 13 | EARNINGS | NZ | NZ_EARNINGS | Done | Done
196 | 14 | EARNINGS | RO | RO_EARNINGS | Done | Done | 0 rows from DISP | 0 rows from DISP
197 |  | USERS | AU | AU_USERS | Done | Done
198 |  | USERS | UA | UA_USERS | Done | Done
199 |  | USERS | LT | LT_USERS | Done | Done
200 |  | USERS | NL | NL_USERS | Done | Done
201 |  | USERS | GR | GR_USERS | Done | Done
202 |  | USERS | DK | DK_USERS | Done | Done
203 |  | USERS | CA | CA_USERS | Done | Done
204 |  | USERS | PT | PT_USERS | Done | Done
205 |  | USERS | IL | IL_USERS | Done | Done
206 |  | USERS | KZ | KZ_USERS | Done | Done | 0 rows from DISP
207 |  | USERS | SE | SE_USERS | Done | Done
208 |  | USERS | IT | IT_USERS | Done | Done
209 |  | USERS | NZ | NZ_USERS | Done | Done
210 |  | USERS | RO | RO_USERS | Done | Done

## Prod Deployment Plan
DCS - Data Ingestion of DCS Adjustment batch 1 - add new columns (export_mode full) | DCS - Data Ingestion of DCS Adjustment batch 2 - add new columns (export_mode full)
devices | profilefields
earnings | promotions
giftcertificates | referralcodepergodfather
orderhistory | seasurveys
orderitems | shipments
orders | spendings
products | touchpoints
users
https://back-office-qa.dcxinge-qa.aws.pmicloud.biz/release/configRelease/91ee09a3-fab6-4b1b-aeb4-e5cc2fa5b607
https://back-office-qa.dcxinge-qa.aws.pmicloud.biz/release/configRelease/b87741bb-eac0-40e3-835d-d08ae0bd8475

## PRD Deployment details
Fullname | Market Code | Category | clean name
edp_consumer_dcs_consumer_dcs_il_devices_lz • edp_consumer | il | devices | edp_consumer_dcs_consumer_dcs_il_devices_lz
edp_consumer_dcs_consumer_dcs_nl_devices_lz • edp_consumer | nl | devices | edp_consumer_dcs_consumer_dcs_nl_devices_lz
edp_consumer_dcs_consumer_dcs_it_devices_lz • edp_consumer | it | devices | edp_consumer_dcs_consumer_dcs_it_devices_lz
edp_consumer_dcs_consumer_dcs_lt_devices_lz • edp_consumer | lt | devices | edp_consumer_dcs_consumer_dcs_lt_devices_lz
edp_consumer_dcs_consumer_dcs_nz_devices_lz • edp_consumer | nz | devices | edp_consumer_dcs_consumer_dcs_nz_devices_lz
edp_consumer_dcs_consumer_dcs_kz_devices_lz • edp_consumer | kz | devices | edp_consumer_dcs_consumer_dcs_kz_devices_lz
edp_consumer_dcs_consumer_dcs_ua_devices_lz • edp_consumer | ua | devices | edp_consumer_dcs_consumer_dcs_ua_devices_lz
edp_consumer_dcs_consumer_dcs_se_devices_lz • edp_consumer | se | devices | edp_consumer_dcs_consumer_dcs_se_devices_lz
edp_consumer_dcs_consumer_dcs_au_devices_lz • edp_consumer | au | devices | edp_consumer_dcs_consumer_dcs_au_devices_lz
edp_consumer_dcs_consumer_dcs_pt_devices_lz • edp_consumer | pt | devices | edp_consumer_dcs_consumer_dcs_pt_devices_lz
edp_consumer_dcs_consumer_dcs_ca_devices_lz • edp_consumer | ca | devices | edp_consumer_dcs_consumer_dcs_ca_devices_lz
edp_consumer_dcs_consumer_dcs_dk_devices_lz • edp_consumer | dk | devices | edp_consumer_dcs_consumer_dcs_dk_devices_lz
edp_consumer_dcs_consumer_dcs_ro_devices_lz • edp_consumer | ro | devices | edp_consumer_dcs_consumer_dcs_ro_devices_lz
edp_consumer_dcs_consumer_dcs_gr_devices_lz • edp_consumer | gr | devices | edp_consumer_dcs_consumer_dcs_gr_devices_lz
edp_consumer_dcs_consumer_dcs_gr_earnings_lz • edp_consumer | gr | earnings | edp_consumer_dcs_consumer_dcs_gr_earnings_lz
edp_consumer_dcs_consumer_dcs_dk_earnings_lz • edp_consumer | dk | earnings | edp_consumer_dcs_consumer_dcs_dk_earnings_lz
edp_consumer_dcs_consumer_dcs_ro_earnings_lz • edp_consumer | ro | earnings | edp_consumer_dcs_consumer_dcs_ro_earnings_lz
edp_consumer_dcs_consumer_dcs_kz_earnings_lz • edp_consumer | kz | earnings | edp_consumer_dcs_consumer_dcs_kz_earnings_lz
edp_consumer_dcs_consumer_dcs_pt_earnings_lz • edp_consumer | pt | earnings | edp_consumer_dcs_consumer_dcs_pt_earnings_lz
edp_consumer_dcs_consumer_dcs_lt_earnings_lz • edp_consumer | lt | earnings | edp_consumer_dcs_consumer_dcs_lt_earnings_lz
edp_consumer_dcs_consumer_dcs_it_earnings_lz • edp_consumer | it | earnings | edp_consumer_dcs_consumer_dcs_it_earnings_lz
edp_consumer_dcs_consumer_dcs_nz_earnings_lz • edp_consumer | nz | earnings | edp_consumer_dcs_consumer_dcs_nz_earnings_lz
edp_consumer_dcs_consumer_dcs_il_earnings_lz • edp_consumer | il | earnings | edp_consumer_dcs_consumer_dcs_il_earnings_lz
edp_consumer_dcs_consumer_dcs_au_earnings_lz • edp_consumer | au | earnings | edp_consumer_dcs_consumer_dcs_au_earnings_lz
edp_consumer_dcs_consumer_dcs_se_earnings_lz • edp_consumer | se | earnings | edp_consumer_dcs_consumer_dcs_se_earnings_lz
edp_consumer_dcs_consumer_dcs_nl_earnings_lz • edp_consumer | nl | earnings | edp_consumer_dcs_consumer_dcs_nl_earnings_lz
edp_consumer_dcs_consumer_dcs_ca_earnings_lz • edp_consumer | ca | earnings | edp_consumer_dcs_consumer_dcs_ca_earnings_lz
edp_consumer_dcs_consumer_dcs_ua_earnings_lz • edp_consumer | ua | earnings | edp_consumer_dcs_consumer_dcs_ua_earnings_lz
edp_consumer_dcs_consumer_dcs_ro_giftcertificates_lz • edp_consumer | ro | giftcertificates | edp_consumer_dcs_consumer_dcs_ro_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_nl_giftcertificates_lz • edp_consumer | nl | giftcertificates | edp_consumer_dcs_consumer_dcs_nl_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_kz_giftcertificates_lz • edp_consumer | kz | giftcertificates | edp_consumer_dcs_consumer_dcs_kz_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_lt_giftcertificates_lz • edp_consumer | lt | giftcertificates | edp_consumer_dcs_consumer_dcs_lt_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_il_giftcertificates_lz • edp_consumer | il | giftcertificates | edp_consumer_dcs_consumer_dcs_il_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_au_giftcertificates_lz • edp_consumer | au | giftcertificates | edp_consumer_dcs_consumer_dcs_au_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_gr_giftcertificates_lz • edp_consumer | gr | giftcertificates | edp_consumer_dcs_consumer_dcs_gr_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_it_giftcertificates_lz • edp_consumer | it | giftcertificates | edp_consumer_dcs_consumer_dcs_it_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_pt_giftcertificates_lz • edp_consumer | pt | giftcertificates | edp_consumer_dcs_consumer_dcs_pt_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_ca_giftcertificates_lz • edp_consumer | ca | giftcertificates | edp_consumer_dcs_consumer_dcs_ca_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_dk_giftcertificates_lz • edp_consumer | dk | giftcertificates | edp_consumer_dcs_consumer_dcs_dk_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_se_giftcertificates_lz • edp_consumer | se | giftcertificates | edp_consumer_dcs_consumer_dcs_se_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_ua_giftcertificates_lz • edp_consumer | ua | giftcertificates | edp_consumer_dcs_consumer_dcs_ua_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_nz_giftcertificates_lz • edp_consumer | nz | giftcertificates | edp_consumer_dcs_consumer_dcs_nz_giftcertificates_lz
edp_consumer_dcs_consumer_dcs_nl_orderhistory_lz • edp_consumer | nl | orderhistory | edp_consumer_dcs_consumer_dcs_nl_orderhistory_lz
edp_consumer_dcs_consumer_dcs_se_orderhistory_lz • edp_consumer | se | orderhistory | edp_consumer_dcs_consumer_dcs_se_orderhistory_lz
edp_consumer_dcs_consumer_dcs_au_orderhistory_lz • edp_consumer | au | orderhistory | edp_consumer_dcs_consumer_dcs_au_orderhistory_lz
edp_consumer_dcs_consumer_dcs_ca_orderhistory_lz • edp_consumer | ca | orderhistory | edp_consumer_dcs_consumer_dcs_ca_orderhistory_lz
edp_consumer_dcs_consumer_dcs_pt_orderhistory_lz • edp_consumer | pt | orderhistory | edp_consumer_dcs_consumer_dcs_pt_orderhistory_lz
edp_consumer_dcs_consumer_dcs_dk_orderhistory_lz • edp_consumer | dk | orderhistory | edp_consumer_dcs_consumer_dcs_dk_orderhistory_lz
edp_consumer_dcs_consumer_dcs_ro_orderhistory_lz • edp_consumer | ro | orderhistory | edp_consumer_dcs_consumer_dcs_ro_orderhistory_lz
edp_consumer_dcs_consumer_dcs_gr_orderhistory_lz • edp_consumer | gr | orderhistory | edp_consumer_dcs_consumer_dcs_gr_orderhistory_lz
edp_consumer_dcs_consumer_dcs_ua_orderhistory_lz • edp_consumer | ua | orderhistory | edp_consumer_dcs_consumer_dcs_ua_orderhistory_lz
edp_consumer_dcs_consumer_dcs_il_orderhistory_lz • edp_consumer | il | orderhistory | edp_consumer_dcs_consumer_dcs_il_orderhistory_lz
edp_consumer_dcs_consumer_dcs_lt_orderhistory_lz • edp_consumer | lt | orderhistory | edp_consumer_dcs_consumer_dcs_lt_orderhistory_lz
edp_consumer_dcs_consumer_dcs_kz_orderhistory_lz • edp_consumer | kz | orderhistory | edp_consumer_dcs_consumer_dcs_kz_orderhistory_lz
edp_consumer_dcs_consumer_dcs_nz_orderhistory_lz • edp_consumer | nz | orderhistory | edp_consumer_dcs_consumer_dcs_nz_orderhistory_lz
edp_consumer_dcs_consumer_dcs_it_orderhistory_lz • edp_consumer | it | orderhistory | edp_consumer_dcs_consumer_dcs_it_orderhistory_lz
edp_consumer_dcs_consumer_dcs_ro_orderitems_lz • edp_consumer | ro | orderitems | edp_consumer_dcs_consumer_dcs_ro_orderitems_lz
edp_consumer_dcs_consumer_dcs_nz_orderitems_lz • edp_consumer | nz | orderitems | edp_consumer_dcs_consumer_dcs_nz_orderitems_lz
edp_consumer_dcs_consumer_dcs_ua_orderitems_lz • edp_consumer | ua | orderitems | edp_consumer_dcs_consumer_dcs_ua_orderitems_lz
edp_consumer_dcs_consumer_dcs_ca_orderitems_lz • edp_consumer | ca | orderitems | edp_consumer_dcs_consumer_dcs_ca_orderitems_lz
edp_consumer_dcs_consumer_dcs_gr_orderitems_lz • edp_consumer | gr | orderitems | edp_consumer_dcs_consumer_dcs_gr_orderitems_lz
edp_consumer_dcs_consumer_dcs_dk_orderitems_lz • edp_consumer | dk | orderitems | edp_consumer_dcs_consumer_dcs_dk_orderitems_lz
edp_consumer_dcs_consumer_dcs_il_orderitems_lz • edp_consumer | il | orderitems | edp_consumer_dcs_consumer_dcs_il_orderitems_lz
edp_consumer_dcs_consumer_dcs_lt_orderitems_lz • edp_consumer | lt | orderitems | edp_consumer_dcs_consumer_dcs_lt_orderitems_lz
edp_consumer_dcs_consumer_dcs_pt_orderitems_lz • edp_consumer | pt | orderitems | edp_consumer_dcs_consumer_dcs_pt_orderitems_lz
edp_consumer_dcs_consumer_dcs_kz_orderitems_lz • edp_consumer | kz | orderitems | edp_consumer_dcs_consumer_dcs_kz_orderitems_lz
edp_consumer_dcs_consumer_dcs_se_orderitems_lz • edp_consumer | se | orderitems | edp_consumer_dcs_consumer_dcs_se_orderitems_lz
edp_consumer_dcs_consumer_dcs_nl_orderitems_lz • edp_consumer | nl | orderitems | edp_consumer_dcs_consumer_dcs_nl_orderitems_lz
edp_consumer_dcs_consumer_dcs_it_orderitems_lz • edp_consumer | it | orderitems | edp_consumer_dcs_consumer_dcs_it_orderitems_lz
edp_consumer_dcs_consumer_dcs_au_orderitems_lz • edp_consumer | au | orderitems | edp_consumer_dcs_consumer_dcs_au_orderitems_lz
edp_consumer_dcs_consumer_dcs_il_orders_lz • edp_consumer | il | orders | edp_consumer_dcs_consumer_dcs_il_orders_lz
edp_consumer_dcs_consumer_dcs_se_orders_lz • edp_consumer | se | orders | edp_consumer_dcs_consumer_dcs_se_orders_lz
edp_consumer_dcs_consumer_dcs_it_orders_lz • edp_consumer | it | orders | edp_consumer_dcs_consumer_dcs_it_orders_lz
edp_consumer_dcs_consumer_dcs_nl_orders_lz • edp_consumer | nl | orders | edp_consumer_dcs_consumer_dcs_nl_orders_lz
edp_consumer_dcs_consumer_dcs_gr_orders_lz • edp_consumer | gr | orders | edp_consumer_dcs_consumer_dcs_gr_orders_lz
edp_consumer_dcs_consumer_dcs_nz_orders_lz • edp_consumer | nz | orders | edp_consumer_dcs_consumer_dcs_nz_orders_lz
edp_consumer_dcs_consumer_dcs_lt_orders_lz • edp_consumer | lt | orders | edp_consumer_dcs_consumer_dcs_lt_orders_lz
edp_consumer_dcs_consumer_dcs_au_orders_lz • edp_consumer | au | orders | edp_consumer_dcs_consumer_dcs_au_orders_lz
edp_consumer_dcs_consumer_dcs_ua_orders_lz • edp_consumer | ua | orders | edp_consumer_dcs_consumer_dcs_ua_orders_lz
edp_consumer_dcs_consumer_dcs_dk_orders_lz • edp_consumer | dk | orders | edp_consumer_dcs_consumer_dcs_dk_orders_lz
edp_consumer_dcs_consumer_dcs_kz_orders_lz • edp_consumer | kz | orders | edp_consumer_dcs_consumer_dcs_kz_orders_lz
edp_consumer_dcs_consumer_dcs_ro_orders_lz • edp_consumer | ro | orders | edp_consumer_dcs_consumer_dcs_ro_orders_lz
edp_consumer_dcs_consumer_dcs_ca_orders_lz • edp_consumer | ca | orders | edp_consumer_dcs_consumer_dcs_ca_orders_lz
edp_consumer_dcs_consumer_dcs_pt_orders_lz • edp_consumer | pt | orders | edp_consumer_dcs_consumer_dcs_pt_orders_lz
edp_consumer_dcs_consumer_dcs_gr_products_lz • edp_consumer | gr | products | edp_consumer_dcs_consumer_dcs_gr_products_lz
edp_consumer_dcs_consumer_dcs_it_products_lz • edp_consumer | it | products | edp_consumer_dcs_consumer_dcs_it_products_lz
edp_consumer_dcs_consumer_dcs_dk_products_lz • edp_consumer | dk | products | edp_consumer_dcs_consumer_dcs_dk_products_lz
edp_consumer_dcs_consumer_dcs_lt_products_lz • edp_consumer | lt | products | edp_consumer_dcs_consumer_dcs_lt_products_lz
edp_consumer_dcs_consumer_dcs_ua_products_lz • edp_consumer | ua | products | edp_consumer_dcs_consumer_dcs_ua_products_lz
edp_consumer_dcs_consumer_dcs_il_products_lz • edp_consumer | il | products | edp_consumer_dcs_consumer_dcs_il_products_lz
edp_consumer_dcs_consumer_dcs_ca_products_lz • edp_consumer | ca | products | edp_consumer_dcs_consumer_dcs_ca_products_lz
edp_consumer_dcs_consumer_dcs_nz_products_lz • edp_consumer | nz | products | edp_consumer_dcs_consumer_dcs_nz_products_lz
edp_consumer_dcs_consumer_dcs_au_products_lz • edp_consumer | au | products | edp_consumer_dcs_consumer_dcs_au_products_lz
edp_consumer_dcs_consumer_dcs_nl_products_lz • edp_consumer | nl | products | edp_consumer_dcs_consumer_dcs_nl_products_lz
edp_consumer_dcs_consumer_dcs_se_products_lz • edp_consumer | se | products | edp_consumer_dcs_consumer_dcs_se_products_lz
edp_consumer_dcs_consumer_dcs_ro_products_lz • edp_consumer | ro | products | edp_consumer_dcs_consumer_dcs_ro_products_lz
edp_consumer_dcs_consumer_dcs_pt_products_lz • edp_consumer | pt | products | edp_consumer_dcs_consumer_dcs_pt_products_lz
edp_consumer_dcs_consumer_dcs_kz_products_lz • edp_consumer | kz | products | edp_consumer_dcs_consumer_dcs_kz_products_lz
edp_consumer_dcs_consumer_dcs_nz_profilefields_lz • edp_consumer | nz | profilefields | edp_consumer_dcs_consumer_dcs_nz_profilefields_lz
edp_consumer_dcs_consumer_dcs_ua_profilefields_lz • edp_consumer | ua | profilefields | edp_consumer_dcs_consumer_dcs_ua_profilefields_lz
edp_consumer_dcs_consumer_dcs_it_profilefields_lz • edp_consumer | it | profilefields | edp_consumer_dcs_consumer_dcs_it_profilefields_lz
edp_consumer_dcs_consumer_dcs_au_profilefields_lz • edp_consumer | au | profilefields | edp_consumer_dcs_consumer_dcs_au_profilefields_lz
edp_consumer_dcs_consumer_dcs_il_profilefields_lz • edp_consumer | il | profilefields | edp_consumer_dcs_consumer_dcs_il_profilefields_lz
edp_consumer_dcs_consumer_dcs_kz_profilefields_lz • edp_consumer | kz | profilefields | edp_consumer_dcs_consumer_dcs_kz_profilefields_lz
edp_consumer_dcs_consumer_dcs_pt_profilefields_lz • edp_consumer | pt | profilefields | edp_consumer_dcs_consumer_dcs_pt_profilefields_lz
edp_consumer_dcs_consumer_dcs_se_profilefields_lz • edp_consumer | se | profilefields | edp_consumer_dcs_consumer_dcs_se_profilefields_lz
edp_consumer_dcs_consumer_dcs_lt_profilefields_lz • edp_consumer | lt | profilefields | edp_consumer_dcs_consumer_dcs_lt_profilefields_lz
edp_consumer_dcs_consumer_dcs_gr_profilefields_lz • edp_consumer | gr | profilefields | edp_consumer_dcs_consumer_dcs_gr_profilefields_lz
edp_consumer_dcs_consumer_dcs_dk_profilefields_lz • edp_consumer | dk | profilefields | edp_consumer_dcs_consumer_dcs_dk_profilefields_lz
edp_consumer_dcs_consumer_dcs_ca_profilefields_lz • edp_consumer | ca | profilefields | edp_consumer_dcs_consumer_dcs_ca_profilefields_lz
edp_consumer_dcs_consumer_dcs_ro_profilefields_lz • edp_consumer | ro | profilefields | edp_consumer_dcs_consumer_dcs_ro_profilefields_lz
edp_consumer_dcs_consumer_dcs_nl_profilefields_lz • edp_consumer | nl | profilefields | edp_consumer_dcs_consumer_dcs_nl_profilefields_lz
edp_consumer_dcs_consumer_dcs_se_promotions_lz • edp_consumer | se | promotions | edp_consumer_dcs_consumer_dcs_se_promotions_lz
edp_consumer_dcs_consumer_dcs_ro_promotions_lz • edp_consumer | ro | promotions | edp_consumer_dcs_consumer_dcs_ro_promotions_lz
edp_consumer_dcs_consumer_dcs_lt_promotions_lz • edp_consumer | lt | promotions | edp_consumer_dcs_consumer_dcs_lt_promotions_lz
edp_consumer_dcs_consumer_dcs_gr_promotions_lz • edp_consumer | gr | promotions | edp_consumer_dcs_consumer_dcs_gr_promotions_lz
edp_consumer_dcs_consumer_dcs_ca_promotions_lz • edp_consumer | ca | promotions | edp_consumer_dcs_consumer_dcs_ca_promotions_lz
edp_consumer_dcs_consumer_dcs_il_promotions_lz • edp_consumer | il | promotions | edp_consumer_dcs_consumer_dcs_il_promotions_lz
edp_consumer_dcs_consumer_dcs_ua_promotions_lz • edp_consumer | ua | promotions | edp_consumer_dcs_consumer_dcs_ua_promotions_lz
edp_consumer_dcs_consumer_dcs_nl_promotions_lz • edp_consumer | nl | promotions | edp_consumer_dcs_consumer_dcs_nl_promotions_lz
edp_consumer_dcs_consumer_dcs_au_promotions_lz • edp_consumer | au | promotions | edp_consumer_dcs_consumer_dcs_au_promotions_lz
edp_consumer_dcs_consumer_dcs_kz_promotions_lz • edp_consumer | kz | promotions | edp_consumer_dcs_consumer_dcs_kz_promotions_lz
edp_consumer_dcs_consumer_dcs_dk_promotions_lz • edp_consumer | dk | promotions | edp_consumer_dcs_consumer_dcs_dk_promotions_lz
edp_consumer_dcs_consumer_dcs_pt_promotions_lz • edp_consumer | pt | promotions | edp_consumer_dcs_consumer_dcs_pt_promotions_lz
edp_consumer_dcs_consumer_dcs_nz_promotions_lz • edp_consumer | nz | promotions | edp_consumer_dcs_consumer_dcs_nz_promotions_lz
edp_consumer_dcs_consumer_dcs_it_promotions_lz • edp_consumer | it | promotions | edp_consumer_dcs_consumer_dcs_it_promotions_lz
edp_consumer_dcs_consumer_dcs_nz_referralcodepergodfather_lz • edp_consumer | nz | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_nz_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_au_referralcodepergodfather_lz • edp_consumer | au | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_au_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_lt_referralcodepergodfather_lz • edp_consumer | lt | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_lt_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_it_referralcodepergodfather_lz • edp_consumer | it | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_it_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_ro_referralcodepergodfather_lz • edp_consumer | ro | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_ro_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_il_referralcodepergodfather_lz • edp_consumer | il | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_il_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_kz_referralcodepergodfather_lz • edp_consumer | kz | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_kz_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_pt_referralcodepergodfather_lz • edp_consumer | pt | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_pt_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_dk_referralcodepergodfather_lz • edp_consumer | dk | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_dk_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_se_referralcodepergodfather_lz • edp_consumer | se | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_se_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_ca_referralcodepergodfather_lz • edp_consumer | ca | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_ca_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_ua_referralcodepergodfather_lz • edp_consumer | ua | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_ua_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_gr_referralcodepergodfather_lz • edp_consumer | gr | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_gr_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_nl_referralcodepergodfather_lz • edp_consumer | nl | referralcodepergodfather | edp_consumer_dcs_consumer_dcs_nl_referralcodepergodfather_lz
edp_consumer_dcs_consumer_dcs_pt_seasurveys_lz • edp_consumer | pt | seasurveys | edp_consumer_dcs_consumer_dcs_pt_seasurveys_lz
edp_consumer_dcs_consumer_dcs_se_seasurveys_lz • edp_consumer | se | seasurveys | edp_consumer_dcs_consumer_dcs_se_seasurveys_lz
edp_consumer_dcs_consumer_dcs_nl_seasurveys_lz • edp_consumer | nl | seasurveys | edp_consumer_dcs_consumer_dcs_nl_seasurveys_lz
edp_consumer_dcs_consumer_dcs_gr_seasurveys_lz • edp_consumer | gr | seasurveys | edp_consumer_dcs_consumer_dcs_gr_seasurveys_lz
edp_consumer_dcs_consumer_dcs_lt_seasurveys_lz • edp_consumer | lt | seasurveys | edp_consumer_dcs_consumer_dcs_lt_seasurveys_lz
edp_consumer_dcs_consumer_dcs_nz_seasurveys_lz • edp_consumer | nz | seasurveys | edp_consumer_dcs_consumer_dcs_nz_seasurveys_lz
edp_consumer_dcs_consumer_dcs_ca_seasurveys_lz • edp_consumer | ca | seasurveys | edp_consumer_dcs_consumer_dcs_ca_seasurveys_lz
edp_consumer_dcs_consumer_dcs_dk_seasurveys_lz • edp_consumer | dk | seasurveys | edp_consumer_dcs_consumer_dcs_dk_seasurveys_lz
edp_consumer_dcs_consumer_dcs_ro_seasurveys_lz • edp_consumer | ro | seasurveys | edp_consumer_dcs_consumer_dcs_ro_seasurveys_lz
edp_consumer_dcs_consumer_dcs_kz_seasurveys_lz • edp_consumer | kz | seasurveys | edp_consumer_dcs_consumer_dcs_kz_seasurveys_lz
edp_consumer_dcs_consumer_dcs_ua_seasurveys_lz • edp_consumer | ua | seasurveys | edp_consumer_dcs_consumer_dcs_ua_seasurveys_lz
edp_consumer_dcs_consumer_dcs_au_seasurveys_lz • edp_consumer | au | seasurveys | edp_consumer_dcs_consumer_dcs_au_seasurveys_lz
edp_consumer_dcs_consumer_dcs_il_seasurveys_lz • edp_consumer | il | seasurveys | edp_consumer_dcs_consumer_dcs_il_seasurveys_lz
edp_consumer_dcs_consumer_dcs_it_seasurveys_lz • edp_consumer | it | seasurveys | edp_consumer_dcs_consumer_dcs_it_seasurveys_lz
edp_consumer_dcs_consumer_dcs_lt_shipments_lz • edp_consumer | lt | shipments | edp_consumer_dcs_consumer_dcs_lt_shipments_lz
edp_consumer_dcs_consumer_dcs_ua_shipments_lz • edp_consumer | ua | shipments | edp_consumer_dcs_consumer_dcs_ua_shipments_lz
edp_consumer_dcs_consumer_dcs_it_shipments_lz • edp_consumer | it | shipments | edp_consumer_dcs_consumer_dcs_it_shipments_lz
edp_consumer_dcs_consumer_dcs_ca_shipments_lz • edp_consumer | ca | shipments | edp_consumer_dcs_consumer_dcs_ca_shipments_lz
edp_consumer_dcs_consumer_dcs_nl_shipments_lz • edp_consumer | nl | shipments | edp_consumer_dcs_consumer_dcs_nl_shipments_lz
edp_consumer_dcs_consumer_dcs_kz_shipments_lz • edp_consumer | kz | shipments | edp_consumer_dcs_consumer_dcs_kz_shipments_lz
edp_consumer_dcs_consumer_dcs_dk_shipments_lz • edp_consumer | dk | shipments | edp_consumer_dcs_consumer_dcs_dk_shipments_lz
edp_consumer_dcs_consumer_dcs_pt_shipments_lz • edp_consumer | pt | shipments | edp_consumer_dcs_consumer_dcs_pt_shipments_lz
edp_consumer_dcs_consumer_dcs_gr_shipments_lz • edp_consumer | gr | shipments | edp_consumer_dcs_consumer_dcs_gr_shipments_lz
edp_consumer_dcs_consumer_dcs_au_shipments_lz • edp_consumer | au | shipments | edp_consumer_dcs_consumer_dcs_au_shipments_lz
edp_consumer_dcs_consumer_dcs_nz_shipments_lz • edp_consumer | nz | shipments | edp_consumer_dcs_consumer_dcs_nz_shipments_lz
edp_consumer_dcs_consumer_dcs_se_shipments_lz • edp_consumer | se | shipments | edp_consumer_dcs_consumer_dcs_se_shipments_lz
edp_consumer_dcs_consumer_dcs_il_shipments_lz • edp_consumer | il | shipments | edp_consumer_dcs_consumer_dcs_il_shipments_lz
edp_consumer_dcs_consumer_dcs_ro_shipments_lz • edp_consumer | ro | shipments | edp_consumer_dcs_consumer_dcs_ro_shipments_lz
edp_consumer_dcs_consumer_dcs_it_spendings_lz • edp_consumer | it | spendings | edp_consumer_dcs_consumer_dcs_it_spendings_lz
edp_consumer_dcs_consumer_dcs_au_spendings_lz • edp_consumer | au | spendings | edp_consumer_dcs_consumer_dcs_au_spendings_lz
edp_consumer_dcs_consumer_dcs_nz_spendings_lz • edp_consumer | nz | spendings | edp_consumer_dcs_consumer_dcs_nz_spendings_lz
edp_consumer_dcs_consumer_dcs_dk_spendings_lz • edp_consumer | dk | spendings | edp_consumer_dcs_consumer_dcs_dk_spendings_lz
edp_consumer_dcs_consumer_dcs_gr_spendings_lz • edp_consumer | gr | spendings | edp_consumer_dcs_consumer_dcs_gr_spendings_lz
edp_consumer_dcs_consumer_dcs_il_spendings_lz • edp_consumer | il | spendings | edp_consumer_dcs_consumer_dcs_il_spendings_lz
edp_consumer_dcs_consumer_dcs_ua_spendings_lz • edp_consumer | ua | spendings | edp_consumer_dcs_consumer_dcs_ua_spendings_lz
edp_consumer_dcs_consumer_dcs_ro_spendings_lz • edp_consumer | ro | spendings | edp_consumer_dcs_consumer_dcs_ro_spendings_lz
edp_consumer_dcs_consumer_dcs_ca_spendings_lz • edp_consumer | ca | spendings | edp_consumer_dcs_consumer_dcs_ca_spendings_lz
edp_consumer_dcs_consumer_dcs_kz_spendings_lz • edp_consumer | kz | spendings | edp_consumer_dcs_consumer_dcs_kz_spendings_lz
edp_consumer_dcs_consumer_dcs_se_spendings_lz • edp_consumer | se | spendings | edp_consumer_dcs_consumer_dcs_se_spendings_lz
edp_consumer_dcs_consumer_dcs_pt_spendings_lz • edp_consumer | pt | spendings | edp_consumer_dcs_consumer_dcs_pt_spendings_lz
edp_consumer_dcs_consumer_dcs_nl_spendings_lz • edp_consumer | nl | spendings | edp_consumer_dcs_consumer_dcs_nl_spendings_lz
edp_consumer_dcs_consumer_dcs_lt_spendings_lz • edp_consumer | lt | spendings | edp_consumer_dcs_consumer_dcs_lt_spendings_lz
edp_consumer_dcs_consumer_dcs_it_touchpoints_lz • edp_consumer | it | touchpoints | edp_consumer_dcs_consumer_dcs_it_touchpoints_lz
edp_consumer_dcs_consumer_dcs_se_touchpoints_lz • edp_consumer | se | touchpoints | edp_consumer_dcs_consumer_dcs_se_touchpoints_lz
edp_consumer_dcs_consumer_dcs_ro_touchpoints_lz • edp_consumer | ro | touchpoints | edp_consumer_dcs_consumer_dcs_ro_touchpoints_lz
edp_consumer_dcs_consumer_dcs_au_touchpoints_lz • edp_consumer | au | touchpoints | edp_consumer_dcs_consumer_dcs_au_touchpoints_lz
edp_consumer_dcs_consumer_dcs_il_touchpoints_lz • edp_consumer | il | touchpoints | edp_consumer_dcs_consumer_dcs_il_touchpoints_lz
edp_consumer_dcs_consumer_dcs_nl_touchpoints_lz • edp_consumer | nl | touchpoints | edp_consumer_dcs_consumer_dcs_nl_touchpoints_lz
edp_consumer_dcs_consumer_dcs_dk_touchpoints_lz • edp_consumer | dk | touchpoints | edp_consumer_dcs_consumer_dcs_dk_touchpoints_lz
edp_consumer_dcs_consumer_dcs_ca_touchpoints_lz • edp_consumer | ca | touchpoints | edp_consumer_dcs_consumer_dcs_ca_touchpoints_lz
edp_consumer_dcs_consumer_dcs_kz_touchpoints_lz • edp_consumer | kz | touchpoints | edp_consumer_dcs_consumer_dcs_kz_touchpoints_lz
edp_consumer_dcs_consumer_dcs_pt_touchpoints_lz • edp_consumer | pt | touchpoints | edp_consumer_dcs_consumer_dcs_pt_touchpoints_lz
edp_consumer_dcs_consumer_dcs_lt_touchpoints_lz • edp_consumer | lt | touchpoints | edp_consumer_dcs_consumer_dcs_lt_touchpoints_lz
edp_consumer_dcs_consumer_dcs_ua_touchpoints_lz • edp_consumer | ua | touchpoints | edp_consumer_dcs_consumer_dcs_ua_touchpoints_lz
edp_consumer_dcs_consumer_dcs_gr_touchpoints_lz • edp_consumer | gr | touchpoints | edp_consumer_dcs_consumer_dcs_gr_touchpoints_lz
edp_consumer_dcs_consumer_dcs_nz_touchpoints_lz • edp_consumer | nz | touchpoints | edp_consumer_dcs_consumer_dcs_nz_touchpoints_lz
edp_consumer_dcs_consumer_dcs_it_users_lz • edp_consumer | it | users | edp_consumer_dcs_consumer_dcs_it_users_lz
edp_consumer_dcs_consumer_dcs_se_users_lz • edp_consumer | se | users | edp_consumer_dcs_consumer_dcs_se_users_lz
edp_consumer_dcs_consumer_dcs_ro_users_lz • edp_consumer | ro | users | edp_consumer_dcs_consumer_dcs_ro_users_lz
edp_consumer_dcs_consumer_dcs_au_users_lz • edp_consumer | au | users | edp_consumer_dcs_consumer_dcs_au_users_lz
edp_consumer_dcs_consumer_dcs_il_users_lz • edp_consumer | il | users | edp_consumer_dcs_consumer_dcs_il_users_lz
edp_consumer_dcs_consumer_dcs_nl_users_lz • edp_consumer | nl | users | edp_consumer_dcs_consumer_dcs_nl_users_lz
edp_consumer_dcs_consumer_dcs_dk_users_lz • edp_consumer | dk | users | edp_consumer_dcs_consumer_dcs_dk_users_lz
edp_consumer_dcs_consumer_dcs_ca_users_lz • edp_consumer | ca | users | edp_consumer_dcs_consumer_dcs_ca_users_lz
edp_consumer_dcs_consumer_dcs_kz_users_lz • edp_consumer | kz | users | edp_consumer_dcs_consumer_dcs_kz_users_lz
edp_consumer_dcs_consumer_dcs_pt_users_lz • edp_consumer | pt | users | edp_consumer_dcs_consumer_dcs_pt_users_lz
edp_consumer_dcs_consumer_dcs_lt_users_lz • edp_consumer | lt | users | edp_consumer_dcs_consumer_dcs_lt_users_lz
edp_consumer_dcs_consumer_dcs_ua_users_lz • edp_consumer | ua | users | edp_consumer_dcs_consumer_dcs_ua_users_lz
edp_consumer_dcs_consumer_dcs_gr_users_lz • edp_consumer | gr | users | edp_consumer_dcs_consumer_dcs_gr_users_lz
edp_consumer_dcs_consumer_dcs_nz_users_lz • edp_consumer | nz | users | edp_consumer_dcs_consumer_dcs_nz_users_lz

## PRD revert to delta
export_mode -> delta
| category name | status | comments
Batch 1 | devices | done
| earnings | done
| giftcertificates | done
| orderhistory | done |  | batch1 | Release - 92615e85-ac61-47bc-b831-c9345c5491af
| orderitems | done |  | batch2 | Release - 2fb592c8-cdde-4d3e-93c4-6cb6677f757c
| orders | done
| products | done
Batch 2 | profilefields | done
| promotions | done | "edp_consumer_dcs_consumer_dcs_gr_promotions_lz" and some object were using different schedule
| referralcodepergodfather | done
| seasurveys | done
| shipments | done
| spendings | done | "dcs_consumer_dcs_dcs_pt_spendings" using different schedule (pt only)
| touchpoints | done
| users | done

## Schedule DISP
Category | Config - UTC | Time (UTC+7) | Time (UTC+7)2
giftcertificates | 0 7 * * ? * | 14:15 | 2 PM
promotions | 0 7 * * ? * | 14:13 | 2 PM
referralcodepergodfather | 0 7 * * ? * | 14:12 | 2 PM
touchpoints | 0 7 * * ? * | 14:13 | 2 PM
seasurveys | 0 9 * * ? * | 16:12 | 4 PM
shipments | 0 9 * * ? * | 16:14 | 4 PM
orders | 20 9 * * ? * | 16:23 | 4 PM
products | 20 9 * * ? * | 16:23 | 4 PM
Devices | 15 10 * * ? * | 17:18 | 5 PM
Earnings | 5 12 * * ? * | 19:14 | 7 PM
spendings | 5 12 * * ? * | 19:11 | 7 PM
orderhistory | 0 14 * * ? * | 21:06 | 9 PM
orderitems | 0 14 * * ? * | 21:03 | 9 PM
profilefields | 0 14 * * ? * | 21:04 | 9 PM
users | 0 14 * * ? * | 21:07 | 9 PM

## Devices (hidden)
No | Order | Entity | Market Code | Table Name | Status Development DEV | Status Development QAS | Comment
1 | 1 | DEVICES | DK | DK_DEVICES | Done | Done
2 | 2 | DEVICES | GR | GR_DEVICES | Done | Done
3 | 3 | DEVICES | RO | RO_DEVICES | Done | Done
4 | 4 | DEVICES | PT | PT_DEVICES | Done | Done
5 | 5 | DEVICES | CA | CA_DEVICES | Done | Done
6 | 6 | DEVICES | IT | IT_DEVICES | Done | Done
7 | 7 | DEVICES | AU | AU_DEVICES | Done | Done
8 | 8 | DEVICES | KZ | KZ_DEVICES | Done | Done | 0 rows from DISP
9 | 9 | DEVICES | LT | LT_DEVICES | Done | Done
10 | 10 | DEVICES | NZ | NZ_DEVICES | Done | Done
11 | 11 | DEVICES | SE | SE_DEVICES | Done | Done
12 | 12 | DEVICES | IL | IL_DEVICES | Done | Done
13 | 13 | DEVICES | NL | NL_DEVICES | Done | Done
14 | 14 | DEVICES | UA | UA_DEVICES | Done | Done
15 | 1 | GIFTCERTIFICATES | SE | SE_GIFTCERTIFICATES | Done | Done | 0 rows from DISP
16 | 2 | GIFTCERTIFICATES | PT | PT_GIFTCERTIFICATES | Done | Done | 0 rows from DISP
17 | 3 | GIFTCERTIFICATES | IT | IT_GIFTCERTIFICATES | Done | Done
18 | 4 | GIFTCERTIFICATES | NL | NL_GIFTCERTIFICATES | Done | Done
19 | 5 | GIFTCERTIFICATES | RO | RO_GIFTCERTIFICATES | Done | Done
20 | 6 | GIFTCERTIFICATES | AU | AU_GIFTCERTIFICATES | Done | Done | 0 rows from DISP
21 | 7 | GIFTCERTIFICATES | DK | DK_GIFTCERTIFICATES | Done | Done | 0 rows from DISP
22 | 8 | GIFTCERTIFICATES | IL | IL_GIFTCERTIFICATES | Done | Done
23 | 9 | GIFTCERTIFICATES | GR | GR_GIFTCERTIFICATES | Done | Done
24 | 10 | GIFTCERTIFICATES | CA | CA_GIFTCERTIFICATES | Done | Done
25 | 11 | GIFTCERTIFICATES | NZ | NZ_GIFTCERTIFICATES | Done | Done | 0 rows from DISP
26 | 12 | GIFTCERTIFICATES | LT | LT_GIFTCERTIFICATES | Done | Done | 0 rows from DISP
27 | 13 | GIFTCERTIFICATES | UA | UA_GIFTCERTIFICATES | Done | Done
28 | 14 | GIFTCERTIFICATES | KZ | KZ_GIFTCERTIFICATES | Done | Done | 0 rows from DISP
29 | 1 | ORDERHISTORY | UA | UA_ORDERHISTORY | Done | Done
30 | 2 | ORDERHISTORY | RO | RO_ORDERHISTORY | Done | Done
31 | 3 | ORDERHISTORY | LT | LT_ORDERHISTORY | Done | Done
32 | 4 | ORDERHISTORY | NL | NL_ORDERHISTORY | Done | Done
33 | 5 | ORDERHISTORY | NZ | NZ_ORDERHISTORY | Done | Done
34 | 6 | ORDERHISTORY | IT | IT_ORDERHISTORY | Done | Done
35 | 7 | ORDERHISTORY | PT | PT_ORDERHISTORY | Done | Done
36 | 8 | ORDERHISTORY | GR | GR_ORDERHISTORY | Done | Done
37 | 9 | ORDERHISTORY | SE | SE_ORDERHISTORY | Done | Done
38 | 10 | ORDERHISTORY | AU | AU_ORDERHISTORY | Done | Done
39 | 11 | ORDERHISTORY | DK | DK_ORDERHISTORY | Done | Done
40 | 12 | ORDERHISTORY | IL | IL_ORDERHISTORY | Done | Done
41 | 13 | ORDERHISTORY | KZ | KZ_ORDERHISTORY | Done | Done | 0 rows from DISP
42 | 14 | ORDERHISTORY | CA | CA_ORDERHISTORY | Done | Done
43 | 1 | ORDERITEMS | AU | AU_ORDERITEMS | Done | Done
44 | 2 | ORDERITEMS | UA | UA_ORDERITEMS | Done | Done
45 | 3 | ORDERITEMS | LT | LT_ORDERITEMS | Done | Done
46 | 4 | ORDERITEMS | NL | NL_ORDERITEMS | Done | Done
47 | 5 | ORDERITEMS | GR | GR_ORDERITEMS | Done | Done
48 | 6 | ORDERITEMS | DK | DK_ORDERITEMS | Done | Done
49 | 7 | ORDERITEMS | CA | CA_ORDERITEMS | Done | Done
50 | 8 | ORDERITEMS | PT | PT_ORDERITEMS | Done | Done
51 | 9 | ORDERITEMS | IL | IL_ORDERITEMS | Done | Done
52 | 10 | ORDERITEMS | KZ | KZ_ORDERITEMS | Done | Done | 0 rows from DISP
53 | 11 | ORDERITEMS | SE | SE_ORDERITEMS | Done | Done
54 | 12 | ORDERITEMS | IT | IT_ORDERITEMS | Done | Done
55 | 13 | ORDERITEMS | NZ | NZ_ORDERITEMS | Done | Done
56 | 14 | ORDERITEMS | RO | RO_ORDERITEMS | Done | Done
57 | 1 | ORDERS | AU | AU_ORDERS | Done | Done
58 | 2 | ORDERS | UA | UA_ORDERS | Done | Done
59 | 3 | ORDERS | LT | LT_ORDERS | Done | Done
60 | 4 | ORDERS | NL | NL_ORDERS | Done | Done
61 | 5 | ORDERS | GR | GR_ORDERS | Done | Done
62 | 6 | ORDERS | DK | DK_ORDERS | Done | Done
63 | 7 | ORDERS | CA | CA_ORDERS | Done | Done
64 | 8 | ORDERS | PT | PT_ORDERS | Done | Done
65 | 9 | ORDERS | IL | IL_ORDERS | Done | Done
66 | 10 | ORDERS | KZ | KZ_ORDERS | Done | Done | 0 rows from DISP
67 | 11 | ORDERS | SE | SE_ORDERS | Done | Done
68 | 12 | ORDERS | IT | IT_ORDERS | Done | Done
69 | 13 | ORDERS | NZ | NZ_ORDERS | Done | Done
70 | 14 | ORDERS | RO | RO_ORDERS | Done | Done
71 | 1 | PROFILEFIELDS | AU | AU_PROFILEFIELDS | Done | Done
72 | 2 | PROFILEFIELDS | UA | UA_PROFILEFIELDS | Done | Done
73 | 3 | PROFILEFIELDS | LT | LT_PROFILEFIELDS | Done | Done
74 | 4 | PROFILEFIELDS | NL | NL_PROFILEFIELDS | Done | Done
75 | 5 | PROFILEFIELDS | GR | GR_PROFILEFIELDS | Done | Done
76 | 6 | PROFILEFIELDS | DK | DK_PROFILEFIELDS | Done | Done
77 | 7 | PROFILEFIELDS | CA | CA_PROFILEFIELDS | Done | Done
78 | 8 | PROFILEFIELDS | PT | PT_PROFILEFIELDS | Done | Done
79 | 9 | PROFILEFIELDS | IL | IL_PROFILEFIELDS | Done | Done
80 | 10 | PROFILEFIELDS | KZ | KZ_PROFILEFIELDS | Done | Done | 0 rows from DISP
81 | 11 | PROFILEFIELDS | SE | SE_PROFILEFIELDS | Done | Done | 0 rows from DISP
82 | 12 | PROFILEFIELDS | IT | IT_PROFILEFIELDS | Done | Done
83 | 13 | PROFILEFIELDS | NZ | NZ_PROFILEFIELDS | Done | Done
84 | 14 | PROFILEFIELDS | RO | RO_PROFILEFIELDS | Done | Done | 0 rows from DISP
85 | 1 | PROMOTIONS | AU | AU_PROMOTIONS | Done | Done | 0 rows from DISP
86 | 2 | PROMOTIONS | UA | UA_PROMOTIONS | Done | Done
87 | 3 | PROMOTIONS | LT | LT_PROMOTIONS | Done | Done
88 | 4 | PROMOTIONS | NL | NL_PROMOTIONS | Done | Done
89 | 5 | PROMOTIONS | GR | GR_PROMOTIONS | Done | Done
90 | 6 | PROMOTIONS | DK | DK_PROMOTIONS | Done | Done
91 | 7 | PROMOTIONS | CA | CA_PROMOTIONS | Done | Done
92 | 8 | PROMOTIONS | PT | PT_PROMOTIONS | Done | Done
93 | 9 | PROMOTIONS | IL | IL_PROMOTIONS | Done | Done
94 | 10 | PROMOTIONS | KZ | KZ_PROMOTIONS | Done | Done | 0 rows from DISP
95 | 11 | PROMOTIONS | SE | SE_PROMOTIONS | Done | Done
96 | 12 | PROMOTIONS | IT | IT_PROMOTIONS | Done | Done
97 | 13 | PROMOTIONS | NZ | NZ_PROMOTIONS | Done | Done
98 | 14 | PROMOTIONS | RO | RO_PROMOTIONS | Done | Done
99 | 1 | SEASURVEYS | AU | AU_SEASURVEYS | Done | Done
100 | 2 | SEASURVEYS | UA | UA_SEASURVEYS | Done | Done | 0 rows from DISP
101 | 3 | SEASURVEYS | LT | LT_SEASURVEYS | Done | Done
102 | 4 | SEASURVEYS | NL | NL_SEASURVEYS | Done | Done
103 | 5 | SEASURVEYS | GR | GR_SEASURVEYS | Done | Done
104 | 6 | SEASURVEYS | DK | DK_SEASURVEYS | Done | Done | 0 rows from DISP
105 | 7 | SEASURVEYS | CA | CA_SEASURVEYS | Done | Done
106 | 8 | SEASURVEYS | PT | PT_SEASURVEYS | Done | Done | 0 rows from DISP
107 | 9 | SEASURVEYS | IL | IL_SEASURVEYS | Done | Done
108 | 10 | SEASURVEYS | KZ | KZ_SEASURVEYS | Done | Done | 0 rows from DISP
109 | 11 | SEASURVEYS | SE | SE_SEASURVEYS | Done | Done | 0 rows from DISP
110 | 12 | SEASURVEYS | IT | IT_SEASURVEYS | Done | Done
111 | 13 | SEASURVEYS | NZ | NZ_SEASURVEYS | Done | Done
112 | 14 | SEASURVEYS | RO | RO_SEASURVEYS | Done | Done | 0 rows from DISP
113 | 1 | SHIPMENTS | AU | AU_SHIPMENTS | Done | Done
114 | 2 | SHIPMENTS | UA | UA_SHIPMENTS | Done | Done | 0 rows from DISP
115 | 3 | SHIPMENTS | LT | LT_SHIPMENTS | Done | Done
116 | 4 | SHIPMENTS | NL | NL_SHIPMENTS | Done | Done
117 | 5 | SHIPMENTS | GR | GR_SHIPMENTS | Done | Done
118 | 6 | SHIPMENTS | DK | DK_SHIPMENTS | Done | Done
119 | 7 | SHIPMENTS | CA | CA_SHIPMENTS | Done | Done
120 | 8 | SHIPMENTS | PT | PT_SHIPMENTS | Done | Done
121 | 9 | SHIPMENTS | IL | IL_SHIPMENTS | Done | Done
122 | 10 | SHIPMENTS | KZ | KZ_SHIPMENTS | Done | Done | 0 rows from DISP
123 | 11 | SHIPMENTS | SE | SE_SHIPMENTS | Done | Done
124 | 12 | SHIPMENTS | IT | IT_SHIPMENTS | Done | Done
125 | 13 | SHIPMENTS | NZ | NZ_SHIPMENTS | Done | Done
126 | 14 | SHIPMENTS | RO | RO_SHIPMENTS | Done | Done
127 | 1 | TOUCHPOINTS | AU | AU_TOUCHPOINTS | Done | Done
128 | 2 | TOUCHPOINTS | UA | UA_TOUCHPOINTS | Done | Done
129 | 3 | TOUCHPOINTS | LT | LT_TOUCHPOINTS | Done | Done
130 | 4 | TOUCHPOINTS | NL | NL_TOUCHPOINTS | Done | Done
131 | 5 | TOUCHPOINTS | GR | GR_TOUCHPOINTS | Done | Done
132 | 6 | TOUCHPOINTS | DK | DK_TOUCHPOINTS | Done | Done
133 | 7 | TOUCHPOINTS | CA | CA_TOUCHPOINTS | Done | Done
134 | 8 | TOUCHPOINTS | PT | PT_TOUCHPOINTS | Done | Done
135 | 9 | TOUCHPOINTS | IL | IL_TOUCHPOINTS | Done | Done
136 | 10 | TOUCHPOINTS | KZ | KZ_TOUCHPOINTS | Done | Done | 0 rows from DISP
137 | 11 | TOUCHPOINTS | SE | SE_TOUCHPOINTS | Done | Done
138 | 12 | TOUCHPOINTS | IT | IT_TOUCHPOINTS | Done | Done
139 | 13 | TOUCHPOINTS | NZ | NZ_TOUCHPOINTS | Done | Done
140 | 14 | TOUCHPOINTS | RO | RO_TOUCHPOINTS | Done | Done
141 | 1 | SPENDINGS | AU | AU_SPENDINGS | Done | Done | 0 rows from DISP
142 | 2 | SPENDINGS | UA | UA_SPENDINGS | Done | Done
143 | 3 | SPENDINGS | LT | LT_SPENDINGS | Done | Done
144 | 4 | SPENDINGS | NL | NL_SPENDINGS | Done | Done | 0 rows from DISP
145 | 5 | SPENDINGS | GR | GR_SPENDINGS | Done | Done | 0 rows from DISP
146 | 6 | SPENDINGS | DK | DK_SPENDINGS | Done | Done
147 | 7 | SPENDINGS | CA | CA_SPENDINGS | Done | Done | 0 rows from DISP
148 | 8 | SPENDINGS | PT | PT_SPENDINGS | Done | Done
149 | 9 | SPENDINGS | IL | IL_SPENDINGS | Done | Done | 0 rows from DISP
150 | 10 | SPENDINGS | KZ | KZ_SPENDINGS | Done | Done | 0 rows from DISP
151 | 11 | SPENDINGS | SE | SE_SPENDINGS | Done | Done | 0 rows from DISP
152 | 12 | SPENDINGS | IT | IT_SPENDINGS | Done | Done | 0 rows from DISP
153 | 13 | SPENDINGS | NZ | NZ_SPENDINGS | Done | Done
154 | 14 | SPENDINGS | RO | RO_SPENDINGS | Done | Done | 0 rows from DISP
155 | 1 | REFERRALCODEPERGODFATHER | AU | AU_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP
156 | 2 | REFERRALCODEPERGODFATHER | UA | UA_REFERRALCODEPERGODFATHER | Done | Done
157 | 3 | REFERRALCODEPERGODFATHER | LT | LT_REFERRALCODEPERGODFATHER | Done | Done
158 | 4 | REFERRALCODEPERGODFATHER | NL | NL_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP
159 | 5 | REFERRALCODEPERGODFATHER | GR | GR_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP
160 | 6 | REFERRALCODEPERGODFATHER | DK | DK_REFERRALCODEPERGODFATHER | Done | Done
161 | 7 | REFERRALCODEPERGODFATHER | CA | CA_REFERRALCODEPERGODFATHER | Done | Done
162 | 8 | REFERRALCODEPERGODFATHER | PT | PT_REFERRALCODEPERGODFATHER | Done | Done
163 | 9 | REFERRALCODEPERGODFATHER | IL | IL_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP
164 | 10 | REFERRALCODEPERGODFATHER | KZ | KZ_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP
165 | 11 | REFERRALCODEPERGODFATHER | SE | SE_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP
166 | 12 | REFERRALCODEPERGODFATHER | IT | IT_REFERRALCODEPERGODFATHER | Done | Done
167 | 13 | REFERRALCODEPERGODFATHER | NZ | NZ_REFERRALCODEPERGODFATHER | Done | Done
168 | 14 | REFERRALCODEPERGODFATHER | RO | RO_REFERRALCODEPERGODFATHER | Done | Done | 0 rows from DISP
169 | 1 | PRODUCTS | AU | AU_PRODUCTS | Done | Done
170 | 2 | PRODUCTS | UA | UA_PRODUCTS | Done | Done
171 | 3 | PRODUCTS | LT | LT_PRODUCTS | Done | Done
172 | 4 | PRODUCTS | NL | NL_PRODUCTS | Done | Done
173 | 5 | PRODUCTS | GR | GR_PRODUCTS | Done | Done
174 | 6 | PRODUCTS | DK | DK_PRODUCTS | Done | Done
175 | 7 | PRODUCTS | CA | CA_PRODUCTS | Done | Done
176 | 8 | PRODUCTS | PT | PT_PRODUCTS | Done | Done
177 | 9 | PRODUCTS | IL | IL_PRODUCTS | Done | Done
178 | 10 | PRODUCTS | KZ | KZ_PRODUCTS | Done | Done | 0 rows from DISP
179 | 11 | PRODUCTS | SE | SE_PRODUCTS | Done | Done
180 | 12 | PRODUCTS | IT | IT_PRODUCTS | Done | Done
181 | 13 | PRODUCTS | NZ | NZ_PRODUCTS | Done | Done
182 | 14 | PRODUCTS | RO | RO_PRODUCTS | Done | Done | 0 rows from DISP
183 | 1 | EARNINGS | AU | AU_EARNINGS | Done | Done | 0 rows from DISP
184 | 2 | EARNINGS | UA | UA_EARNINGS | Done | Done
185 | 3 | EARNINGS | LT | LT_EARNINGS | Done | Done
186 | 4 | EARNINGS | NL | NL_EARNINGS | Done | Done | 0 rows from DISP
187 | 5 | EARNINGS | GR | GR_EARNINGS | Done | Done | 0 rows from DISP
188 | 6 | EARNINGS | DK | DK_EARNINGS | Done | Done | 0 rows from DISP
189 | 7 | EARNINGS | CA | CA_EARNINGS | Done | Done
190 | 8 | EARNINGS | PT | PT_EARNINGS | Done | Done
191 | 9 | EARNINGS | IL | IL_EARNINGS | Done | Done | 0 rows from DISP
192 | 10 | EARNINGS | KZ | KZ_EARNINGS | Done | Done | 0 rows from DISP
193 | 11 | EARNINGS | SE | SE_EARNINGS | Done | Done | 0 rows from DISP
194 | 12 | EARNINGS | IT | IT_EARNINGS | Done | Done
195 | 13 | EARNINGS | NZ | NZ_EARNINGS | Done | Done
196 | 14 | EARNINGS | RO | RO_EARNINGS | Done | Done | 0 rows from DISP